## Sheet1
#VALUE!
Step # | Task Name | Story Points | Developer | Quarter
1.1–1.2 | Login automation (open system + credentials) | 5 | Dev1 | Q1
1.3–1.4 | Dashboard navigation & WI3 iteration loop | 8 | Dev2 | Q1
1.4.A–1.4.D | Work Item details + PDF handling (open, download, extract) | 8 | Dev3 | Q2
1.4.E–1.4.H | Vendor search flow (navigate, enter Tax ID, search) | 3 | Dev4 | Q2
1.4.I (Yes Path) | Vendor exists: add invoice details + update WI | 8 | Dev2 | Q2
1.4.I (No Path) | Vendor not found: reject WI + send escalation email | 8 | Dev5 | Q2
1.4.J | Check for more WI3 items & close system | 3 | Dev6 | Q2
Support | Cross-cutting support: exception handling, logging, testing, deployment, KT | 5 | Dev6 + All | Q3
Overall: Complexity = Medium- ~25 per sprint (48 overall with support tasks)
Delivery Timeline = ~1 months (assuming steady team velocity & no blockers)
Team size: 6 developers (parallel work, but some dependencies)