## Sheet1
S.No | Issue/Change | Issue Raised On | Analysis | Issue Type | Action Owner | Status | ETA | Comments
1 | Slowness of VM causing performance issues during BOT runs. | 2022-08-05 | RAM usage was high during BOT runs. | TS setup not adequate | Client | Closed |  | RAM increased to 32 GB by client on 08/12.
2 | Input report not picked up by bot correctly | 2023-08-07 | Report name has a "-" missing because of which bot was not able to pick it up as it was searching for the Title per the naming convention mentioned in PDD | Issue | Client | Closed |  | Report name changed